## Sheet1
TimeLine | Start Date | End Date | Duration
Discussion about implementation | 2021-02-03 | 2021-02-05 | 2
Repository Inatialisation | 2021-02-03 | 2021-02-05 | 2
CSV File Created | 2021-02-10 | 2021-02-12 | 2
Tournament Class Created | 2021-02-15 | 2021-02-22 | 7
Team Class Created | 2021-02-15 | 2021-02-24 | 9
Randomiser Class Created | 2021-02-15 | 2021-02-26 | 11
Testing | 2021-03-01 | 2021-03-04 | 3
First Prototype | 2021-03-08 | 2021-03-10 | 2
Resolving any issues | 2021-03-11 | 2021-03-12 | 1
Implenting any changes required | 2021-03-15 | 2021-03-19 | 4
2nd Phase Testing | 2021-03-22 | 2021-03-26 | 4
Updates and fixes | 2021-03-29 | 2021-03-31 | 2
finalised Prototype | 2021-04-01 | 2021-04-05 | 4
Submissions | 2021-04-09 | 2021-04-10 | 1
PERT CHART DATA | Optimistic time(O) | Pessemistic Time(P) | Most Likely Time(M) | Expected | EXPECTED INT | PERT FORMULA
Discussion about implementation | 1 | 3 | 2 | 1.66… | 2 | (O + (4*M) + P) / 6
Repository Inatialisation | 1 | 3 | 2 | 1.66… | 2
CSV File Created | 1 | 3 | 2 | 1.66… | 2
Tournament Class Created | 5 | 9 | 7 | 7.16… | 7
Team Class Created | 8 | 11 | 9 | 9.16… | 9
Randomiser Class Created | 9 | 13 | 11 | 11 | 11
Testing | 2 | 4 | 3 | 3 | 3
First Prototype | 1 | 3 | 2 | 1.66… | 2
Resolving any issues | 1 | 2 | 1 | 1.16… | 1
Implenting any changes required | 3 | 5 | 4 | 4 | 4
2nd Phase Testing | 2 | 5 | 4 | 3.833.. | 4
Updates and fixes | 1 | 3 | 2 | 1.66… | 2
finalised Prototype | 2 | 5 | 4 | 3.833.. | 4
Submissions | 1 | 1 | 1 | 1 | 1